## To-Do List
Category | Task | Priority | Importance | Urgency | Responsible | Start Date | Due Date | % Complete | Status | Notes
What is ESG | Budget | Normal |  |  | David | 2022-07-27 | #REF! | 0% | #REF!
| Promotional Description | High |  |  | Winnie | 2022-07-27 | 2022-08-10 | 0% | #REF!
| Production House | Low |  |  | Winnie | 2022-07-27 | 2022-08-10 | 0% | #REF!
| Interview Questions |  |  |  | Alex | 2022-07-27 |  |  | #REF!
| Zoom Replay |  |  |  |  | 2022-07-27 |  |  | #REF!
| Follow up on international chapters |  |  |  | jojo | 2022-07-27 | 2022-09-30 |  | #REF!
| Backup plan for international chapters |  |  |  | Winnie | 2022-07-27 |  |  | #REF!
| Follow up with NWD |  |  |  | Alex | 2022-07-27 |  |  | #REF!
| Follow up with Ocean Park |  |  |  | Alex
| Plan Logistic |  |  | Low |  | 2022-07-27 | 2022-09-10 |  | #REF!
| Prepare for video shooting | High |  | Normal
Into the Metaverse | Budget |  |  |  |  | 2022-07-27 |  |  | #REF!
| Promotion Description |  |  |  | winnie | 2022-07-27 |  |  | #REF!
| Ask for promotion materials with HKUST |  |  |  |  | 2022-07-27 |  |  | #REF!
| Pre recording |  |  |  |  | 2022-07-27 |  |  | #REF!
| Zoom replay technical considerations |  |  |  |  | 2022-07-27 |  |  | #REF!
| Add watermark item | High |  | Low | Joel | 2022-10-20
Invest HK + GBA Intro | Budget |  |  |  |  | 2022-07-27 |  |  | #REF!
| Promotion Description |  |  |  | winnie | 2022-07-27 |  |  | #REF!
| Production House |  |  |  | winnie | 2022-07-27 |  |  | #REF!
| Program Rundown Moderator Guest speaker Venue Within Aug |  |  |  |  | 2022-07-27 |  |  | #REF!
[6 empty] | 2022-07-27 |  |  | #REF!
|  | Normal |  |  |  | #REF! | #REF! | 0% | #REF!
[6 empty] | 2022-07-27 |  |  | #REF!
[6 empty] | 2022-07-27 |  |  | #REF!
| Interview Questions |  |  |  |  | 2022-07-27 |  |  | #REF!
| Follow up with JLL | [7 empty] | #REF!
Business Networking | Budget | [7 empty] | #REF!
| Promotion Description |  |  |  | winnie |  |  |  | #REF!
| Venue |  |  |  | winnie |  |  |  | #REF!
| Venue Quote - Mira |  |  |  | Alex
| Venue Quote - Shangri La |  |  |  | David
| Program Rundown |  |  |  | Winnie |  |  |  | #REF!
| Registration | [7 empty] | #REF!
| Registration - Follow Up Payment |  |  |  | Alex
Registration - Draft Reminder Mesage
| Backup plan | [7 empty] | #REF!
| Quote Stickers |  |  |  | David
Helper List
Registration List
| Promote FB |  |  |  | Everyone
| Promote PM Whatsapp |  |  |  | Everyone
| Ask Protocol |  |  |  | Joel
MC Coordination
Seat arrangement
Name Badge
Business in the Air | Budget | [7 empty] | #REF!
| Promotion Description |  |  |  | winnie |  |  |  | #REF!
| Production house |  |  |  | winnie
| Provide promotion video - Provide promo video - Align JVC registration | [7 empty] | #REF!
| Video Submission |  |  |  |  | 2022-09-01 | 2022-10-12 |  | #REF!
| Video for production house to edit |  |  |  |  | 2022-10-13 | 2022-10-20 |  | #REF!
| Video review |  |  |  |  | 2022-10-20 | 2022-10-27
| Program Rundown | [7 empty] | #REF!
Promote videos